## Sheet1
Start Date of Project: |  | 09.12.14
End Date of Project: |  | 10.12.14
CRUD operations using Spring
SL No | Module Name | Sub-module Name | Task | Assigned to | Start Date | Estimated Time (ETA) | Completion Date | Day(s) Needed | Day(s) Taken | Remarks | Reason
1 | Login Authentication | Login Page | Create Login Page(Login.jsp) | Khalid | 2014-09-12 | 1 day |  |  | 1 day
|  | Login Controller | Create Controller Page | Khalid | 2014-09-13 | 1 day |  |  | 1 day
2 | User info | User Registration | Add user info | Raju | 2014-09-12 | 1 day |  |  | 1 day
|  |  | Update user info | Raju | 2014-09-13 | 1 day |  |  | 1 day
|  |  | Delete user info | Hasan | 2014-09-12 | 1 day |  |  | 1 day
|  |  | Display User Info | Hasan | 2014-09-13 | 1 day |  |  | 1 day